## Sheet1
Option Period
| 2010 | [8 empty] | 2011
Tasks/Use Case/Milestones |  | May | June | July | August | September | October | November | December |  | January | February
Releases
[5 empty] | C3PR v2.9.1/CCTS 2.2 | [6 empty] | C3PR v2.9.3/CCTS 2.3
Standard and Compliance Support
ECCF Review | [10 empty] | start
BAM 1.1 Harmonization |  |  | start | complete
BRIDG 3.1 Harmonization |  | ongoing | ongoing | complete
Support 21 CFR Part 11 requirements | [11 empty] | start
Support HIPPA requirements | [11 empty] | start
Support section 508 requirements | [11 empty] | start
Enterprise Service Integration and Support
Support Person Service |  |  |  |  | start | ongoing | ongoing | complete
Support Organization Service |  |  |  |  | start | ongoing | ongoing | complete
Support Protocol Abstraction Service |  |  |  |  | start | ongoing | ongoing | complete
Suite Support
Build Deployment Automation (BDA) |  | ongoing | ongoing | complete
New Suite Use Cases |  |  |  |  | start | ongoing | ongoing | ongoing | ongoing |  | ongoing | complete
Implement Common Security Framework |  | ongoing | ongoing | complete
Enterprise Service Development
Subject Management Service |  | ongoing | ongoing | ongoing | ongoing | complete
Subject Registration Service |  | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing |  | ongoing | ongoing
Randomization Service |  | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing |  | ongoing | ongoing
caTISSUE Integration | [5 empty] | start | ongoing | ongoing | ongoing |  | ongoing | ongoing
Use Case
Flexible Reporting (Advacned Search) |  | ongoing |  |  | ongoing | ongoing | ongoing | ongoing | ongoing |  | complete
Subject Demographic snapshot |  | complete
Multiple 'off-epoch' primary and secondary reason codes |  | ongoing | ongoing | complete
Reconsent |  |  | ongoing | complete
Consent Form |  |  | ongoing | complete
Multiple organizations for reseach staff |  | ongoing | complete
Custom fields |  |  |  |  | ongoing | complete
OPEN Integration - part of NES or custom services | [6 empty] | start | ongoing | ongoing |  | ongoing | ongoing
Create study templates | [6 empty] | prioritize
Eligibility Guidelines | [6 empty] | prioritize
Link/upload documents | [6 empty] | prioritize
Merge subjects | [6 empty] | prioritize
Custom disease (right now CTEP) and custom disease sites (right now ICD9 CM) | [6 empty] | prioritize
Subject can be placed on a non enrolling epoch even if the study is not opened | [6 empty] | prioritize
*Subject study progression history | [6 empty] | prioritize
Customize status names | [6 empty] | prioritize
Tracking on a per study basis | [6 empty] | prioritize
Store more than one address for subject | [6 empty] | prioritize
Enhance Address and contact information of subjects | [6 empty] | prioritize
Request ability to centrally administer the text presented for each status | [6 empty] | prioritize
Multiple Registrations for the same subject to the same trial | [6 empty] | prioritize
Basic Science Eligibility Criteria | [6 empty] | prioritize
Flexible business rules | [6 empty] | prioritize
Organization Networks | [6 empty] | prioritize
Hosted mode – security, data element protection | [6 empty] | prioritize
Support more flexible internal book modifications | [6 empty] | prioritize
Configurable subject identifiers | [6 empty] | prioritize
*De-identification | [6 empty] | prioritize
*Site to site transfer of subject | [6 empty] | prioritize
*Moving subject to new version of study | [6 empty] | prioritize
(*These were prioritized as high priority use cases)
Deployment Support
Support installer enabled upgrade/fresh install of system |  | start | ongoing | ongoing | ongoing | ongoing | complete
Adopter Activity
Review Test Plan |  |  | start (All) | complete (All)
Perform User Acceptance Testing |  |  | start (All) | complete (All) | ongoing (Mayo, BCM) | ongoing (Mayo, BCM) | ongoing (Mayo, BCM) | ongoing (Mayo, BCM) | ongoing (Mayo, BCM) |  | ongoing (Mayo, BCM) | ongoing (Mayo, BCM)
Perform Pilot Testing |  |  | start (WFU) | ongoing (WFU) | ongoing (WFU) | ongoing (WFU) | ongoing (WFU) | ongoing (WFU) | ongoing (WFU) |  | ongoing (WFU) | ongoing (WFU)
Review Use Cases and System Requirements Specification, including service specifications. |  | ongoing (All) | ongoing (All) | ongoing (All) | ongoing (All) | ongoing (All) | ongoing (All) | complete
Usability Testing |  |  | start (All) | ongoing (All) | ongoing (All) | ongoing (All) | ongoing (All) | ongoing (All) | ongoing (All) |  | ongoing (All) | ongoing (All)
KC Support |  | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing | ongoing |  | ongoing | ongoing
Training and Documentation
Update Technical Configuration Guide |  | update document | update document | update document | update document | update document | update document | update document | update document |  | update document | complete
Update Installation Guide |  | update document | update document | update document | update document | update document | update document | update document | update document |  | update document | complete
Update User Guide |  | update document | update document | update document | update document | update document | update document | update document | update document |  | update document | complete
Update Admin Guide |  | update document | update document | update document | update document | update document | update document | update document | update document |  | update document | complete
Update API documentation |  | update document | update document | update document | update document | update document | update document | update document | update document |  | update document | complete
Develop training materials |  | update document | update document | update document | update document | update document | update document | update document | update document |  | update document | complete
Update on-line help to reference KC wiki - End User Guide |  | update document | update document | update document | update document | update document | update document | update document | update document |  | update document | complete
Project Management
Vision and Scope document |  | update document |  |  |  |  | update document |  |  |  |  | complete
Project Plan |  | create plan | update plan | update plan | update plan | update plan | update plan | update Plan | update Plan |  | update plan | update plan
Reports (Status and Financial) |  | monthly report Submitted | monthly report Submitted | monthly report Submitted | monthly report Submitted | monthly report Submitted | monthly report Submitted | monthly report Submitted | monthly report Submitted |  | monthly report Submitted | monthly report Submitted